## Tender Status
AWARDED TENDERS of GM(RF NW)MS UNIT DURING 2009-2010
SL. | UNIT | Item / Nature of Work. | Tender Number & Dt. | Mode of Tender Enquiry | Estimated Quantity. | Estimated Tender Value. | Date of Publication of NIT. | Type of Bidding (Single/ two) | Last Date, Receipt of Tender | Tender Due Oepned | Nos. of Tenders Received | Tender Validity Upto | TEC on Tech. Bid. | Nos. & Name of Parties qualified after Technical Evaluation. | Nos. & Name of Parties NOT Qualified After Technical Evaluation. | Price bid Opened On | TEC on Price Bid. | Negotiation on L1 bid | LOA/LOO issued on | P.O. issued on | Whether Contract Awarded to Lowest Tender/Evaln. | P.O./Contract No. & Date. | Name/s of Contractor. | P.O. Quantity. | Approved Rate (Rs.) | Value of Contract / P.O. | Scheduled Date/s of Supplly. Or REMARK.
1 | DE(P-1)MS | Supply & Installation of 6M poles, Cable Tray, Aviation Lamps and Lightning Arrestors | MTNL/DE(Project-1) MS/Tender/Motorola/2G-Installation/2009-10 Dt. 16.06.2009 | Open | 6M Poles-210 Cable Tray-1200Mtrs Avaition Lamps-70 Lightning Arrestors-280 | 40,23,090 | 19/6/2009 | Two Bid. | 2009-10-07 | 13/7/2009 | 3 | 210 days | 23/7/2009 & 27/7/2009 | (1) M/s N RAJ Industries (2) M/s TCIL | (1) M/s Good Will Telecom Infra | 24/8/2009 | 27/8/2009 | 2009-12-10 | MTNL/MUMBAI/DE(Project-2) MS/APO/Poles,CT,AL & LA/09-10 dt 26/11/2009 | 14/12/2009 for first BTS site. | Yes, on negotiatred rate. | P-01 dt:-14/12/09 | 1)N RAJ Industries | APO Quantity 6M Poles-147 Cable Tray-840Mtrs Avaition Lamps-49 Lightning Arrestors-196 | 6M Pole-Rs. 17823.84 Cable Tray/mtr-Rs.720.75 Avaition Lamp-Rs.8354.92 Lightning Arrestor-Rs.1281.08 | APO Value Rs. 38,86,017/- | 13/12/2010
2 | DE(P-2)MS | Supply & Installation of I-beam, Foundation, Earthing sysem, installation of Motorola Outdoor BTS, Power Plant and Batteries at 105 sites in GSM area of MTNL Mumbai. | MTNL/DE(Project-2) MS/Tender/Motorola/105 OD BTS/2009-10 Dt. 22.07.2009 | Open | 105 BTS sites | 1,56,00,000 | 25/7/2009 | Two Bid. | 18/8/2009 | 18/08/2009 | 3 | 210 days | 25/8/2009 | (1) M/s GTL (2) M/s TCIL | (1) M/s Good Will Telecom Infra | 2009-03-09 | 2009-11-09 | No | MTNL/MUMBAI/DE(Project-2) MS/APO/105 OD BTS/09-10 dt 31/10/2009 | 5/12/2009 for first BTS site. | Yes | P-01 Dt:-05/12/09 | (1) M/s GTL ltd. (2) M/s TCIL | APO Quantity 73 BTS sites - GTL 32 BTS sites - TCIL | Rs.1,55,221 per site | APO Value GTL-Rs.1,13,31,133. TCIL-Rs.49,67,072. | 16/11/2010