## Finalised Tender (2012-13) List
REPORT OF TENDERS FINALISED (MONTHWISE) DURING 2012-2013 UNIT NAME : GM(MM), MUMBAI.
Month | Sl. | eps Tender ID | UNIT | Item / Nature of Work. | Tender Number & Dt. | Mode of Tender Enquiry | Estimated Quantity. | Estimated Tender Value. | Date of Publication of NIT. | Type of Bidding (Single/ two) | Last Date, Receipt of Tender | Tender Due Opned | Nos. of Tenders Received | Tender Validity Upto (Days) | Nos. & Name of Parties qualified after Technical Evaluation. | Nos. & Name of Parties NOT Qualified After Technical Evaluation. | Price bid Opened On | APO/LOA/ LOO issued on | P.O. issued on | Whether Contract Awarded to L1 | P.O./Contract No. & Date. | Name/s of Contractor. | P.O. Quantity. | Approved Basic Rate (Rs.) | Value of Contract / P.O. | Scheduled Date/s of Supplly. Or REMARK. | Total value of P.O
April, 2012 | 1 | 112 | SM(MM-II) | PVC TWIN WIRE (0.5mm) | MTNM/MM-II/ SDE (TIPC-I)/ 15-43/2011-12 | Open. | 2760 Kms | 82,22,619.60/- | 04-10-2011' | Two | 08-11-2011' | 09-11-2011' | 3 | 150 | 1) Mentor cables 2) Nisha cables 3) Surya cables | NIL | 03-01-2012' | ---' | 05-03-2012 & 30/04/2012. | YES | PO-01 Date:-30/04/12 PO-02 Date:-30/04/12 PO-08 Dte:-28/03/12 | 1)Mentor cable 2)Nisha cable 3)Surya cables | 1)689 Kms 2)691 Kms 3)1380 Kms | Rs.2864/- | Rs. 23,01,997.23 Rs. 23,08,679.37 Rs. 46,10,676.60 | 11/06/2012 | Rs. 92,21,353.20
| 2 | 120 | SM(MM-VI) | CONTINEOUS COMPUTERS STATIONARY EZR Blank pepar (70 GSM) | MTNM/AGM(MM-VI)/SDE(P &S)/41-30/2010-11 | Open. | As per section V | 8,01,010.30/- | 29-09-2011' | Two | 24-10-2011' | 25-10-2011' | 2 | 150 | 1)Shivam Book Mfg. 2)Taiyo Business ltd | NIL | 03-12-2011' | LOA 09-02-2012 | R/C 20/04/2012 | YES | R/C No. MTNL/AGM(M-VI)/SDE(P&S)/RCT/41-30/2010-11 DTD. 20/4/2012. | M/s Shivam Book MFG. Co. | R/c | (1) 289.28 (2) 646.38 (3) 1047.38 (4) 428.93 (5) 947.63 | Rs. 876714.6 | R/C | 876714.6
May, 2012 | 3 | 131 | SM(MM-II) | KRONE MAKE INSERTION TOOL | MTNM/MM-II/ DM(TICP-II)/14-07/ 11-12 | Open. | 1500 Nos | 13,85,716/- | 01-11-2011' | Two | 20-12-2011' | 22-12-2011' | 3 | 150 | 1)Digital Hi ways pvt ltd | 1) Spectra Conn pvt ltd 2) Mamta Elect & Comm. | 27-03-2012' | 2012-05-18 | 31-05-2012' | Yes | P-04 Date:-31/05/12 | 1)Digital Hi-Ways ltd. | 1500 Nos | Rs.862/- | Rs.14,39,141.33 | 30/06/2012 | Rs. 14,39,141.33
June, 2012 | 4 | 116 | SM(MM-III) | Buttinski Telephone Handset with CAMC | SM(MM-III)/BTH/13-64/2011-12 | Open. | 3000 Nos | 18,16,710/- | 03-11-2011' | Two | 21-12-2011' | 21-12-2011' | 1 | 150 | 1)Eltech Enterprises | NIL | 06-02-2012' | 2012-05-21 | 08-06-2012' | Yes | T-01 Date:-08/06/12 | 1)Eltech Enterprises | 3000 Nos | Rs.637.20 | Rs.19,11,600/- | 31/10/2012 | Rs. 19,11,600/-
| 5 | 104 | SM(MM-II) | JELLA COMPOUND | MTNM(MM-II)/ SDE(I&C)16-13(A)/ 2011-12 | Open. | 8000 Kg | 36,02,880/- | 18-11-2011' | Two | 02-01-2012' | 02-01-2012' | 2 | 150 | 1) Aruna Enterprises 2) 3S Petrochem | N/A | 24-04-2012' | 2012-05-17 | 04-06-2012' | Yes | PO-07, Dt:-04/06/12 PO-03 Dt:- 04/06/12 | 1) 3S Petrochem 2)Aruna Enterpris. | 1)1800 Kg 2) 4200 Kg | 1)Rs.478.90 | 1)9,39,600/- 2)21,92,400/- | 1)18/07/2012 2)26/07/2012 | Rs. 31,32,000/-
| 6 | 111 | SM(MM-VI) | S-97 (File cover )& APP-19 (CR File cover) | MTNM/AGM(MM-I)/ SDE(P&S)/13-01/ 2010-11 | Open. | 1) 1,00,000 Nos 2) 2000 Nos | 5,79,180/- | 03-11-2011' | Two | 07-12-2011' | 08-12-2011' | 1 | 150 | 1) Shivam Book mfg | N/A | 14-02-2012' | ---' | 16-07-2012' | Yes | PO-01 Dt:-16/07/12 | 1) Shivam Book mfg | 1)100000 Nos 2)2000 Nos | 1)Rs.5.12 2)Rs.5.70 | Rs,5,49,980/- | 07-09-2012' | Rs, 5,49,980/-
| 7 | 163 | SM(MM-II) | JT/KIT TSF-4 | MTNM/MM-II/ SDE(I&C)/16-13/ 2011-12 | Open. | 2200 Nos | 16,01,490/- | 28-12-2011' | Two | 21-02-2012' | 21-02-2012' | 4 | 150 | 1) Jas Tech 2) Rohit Corp 3) Sunrise Tele. 4) Meritronics Pvt ltd | NIL | 30-04-2012' | 2012-06-08 | 09-07-2012' | Yes | 1)P-09 Dt:-09/07/12 | 1)Merritronics pvt ltd | 1)1540 Nos | Rs.820.63 | Rs.13,76,185.89 | 20-08-2012' | Rs. 13,76,185.89
July, 2012 | 8 | 188 | SM(MM-II) | JT/KIT TSF-2 | MTNM/MM-II/ SDE(I&C)/16-13/ 2011-12 | Open. | 600 Nos | 1,63,158/- | 20-01-2012' | Two | 03-03-2012' | 05-03-2012' | 4 | 150 | 1)Meritronics Pvt ltd | 1) Jas Tech 2) Rohit Corpo 3) Sunrise Tele | 04-05-2012' | 2012-07-07 | 21-07-2012' | Yes | 1)P-11 Dt:-21/07/12 | 1)Merritronix Pvt Ltd | 1)600 Nos | Rs.411.93 | 1)Rs.2,71,025.28 | 27-08-2012' | Rs. 2,71,025.28
| 9 | 189 | SM(MM-II) | JT/KIT TSF-3 | MTNM/MM-II/SDE(I&C)/16-13/ 2011-12 | Open. | 2000 Nos | 6,84,700/- | 12-01-2012' | Two | 23-02-2012' | 24-02-2012' | 3 | 150 | 1)Meritronics Pvt ltd | 1) Jas Tech 3) Sunrise Tele | 28-04-2012' | 2012-06-07 | 06-07-2012' | Yes | 1)P-08 Dt:-06/07/12 | 1)Merritronix Pvt Ltd | 1)1000Nos | Rs.495.68 | 1)Rs.5,43,947.45 | 16-08-2012' | Rs. 5,43,947.45
| 10 | 76 | SM(MM-III) | EPBT with LJU | AGM(MM-III).13-44/ EPBT/2011-12/01 | Open. | 175000 Nos | 3,91,14,250/- | 05-12-2011' | Two | 12-01-2012' | 12-01-2012' | 4 | 150 | 1) Pramod Tel,ltd 2) ITI ltd. 3) Beetel Teletech 4) SRV Tele pvt ltd, | 1) ITI LTD | 10-04-2012' | 2012-06-18 | 26-07-2012' | Yes | T-04 Dt:-26/07/12 | 1)SRV Telecom Pvt. | 1)65625 Nos | Rs.234.66 | Rs.1,53,99,562.50 | 05-01-2013' | Rs. 1,53,99,562.50
| 11 | 118 | SM(MM-III) | SHDSL modem with COT | SM(MM-III)/SHDSL/ 2011-12 | Open. | 150 Pairs | 16,71,986/- | 28-01-2012' | Two | 07-03-2012' | 07-03-2012' | 5 | 150 | 1) Team Eng 2) Attire Tech | 1) Precision Elec 2) Nomus Comm system 3) Natelco infotech. | 07-06-2012' | 2012-07-16 | 24-07-2012' | Yes | T-08 Dt:-24/07/12 | 1)Team Engineers 2)Nomus Comm | 1)105 Pairs 2)45 Pairs | Rs.8506/- | Rs.10,23,591.45 Rs.438682.05 | 25-08-2012 19-10-12' | Rs.10,23,591.45 Rs.438682.05
Aug., 2012 | 12 | 147 | SM(MM-III) | SMF VRLA BATTERY. (1) 48V/200AH (2) 48V/400AH (3) 48V/600AH (4) 48V/1000AH (5) 48V/1500AH (6) 48V/2000AH (7) 48V/4000AH | SM(MM-III)/BAT/ 12-63/2011-12/2 | Open. | 132 Sets | 2,31,14,946.84 | 06-02-2012' | Two | 16-03-2012' | 16-03-2012' | 3 | 150 | 1) Exide Indusries 2) ARBL 3) Energy leader batt. | NIL | 28-04-2012' | 2012-07-13 | 09-08-2012' | yes | MMBY/T-09/BAT/ 12-13 DT-09-08-12 | M/S Energy Leaders Battery India Ltd. | 59 | (1) 58862.26 (2) 110743.07 (3) 166189.61 (4) 27692.68 (5) 415474.02 (6) 553965.36 (7) 1107930.72 | 19063394 | 15-10-2012' | Rs. 19063394.00
| 13 | 110 | SM(MM-II) | IDC Module 10 Pr. 0.5mm (Connection type) | MTNN/MM-II/ DM(TICP-II)/14-26/ 2011-12 | Open. | 75,000 Nos | 27,30,000/- | 09-01-2012' | Two | 28-02-2012' | 29-02-2012' | 2 | 150 | 1) Malson Electronics | 1) indian Tele & Electric co | 09-05-2012' | 6.8.12 | 31.8.12' | YES | 31-08-2012' | Malason Electronics | 75000 | 45.5 | Rs.3583500/- | 15-02-2013 ' | Rs. 3583500/-
| 14 | 148 | SM(MM-II) | H/W PVC 10 PR CABLE | MTNM/MM-II/SDE(TIPC-I)/15-85/2011-12 | Open. | 100 Kms | 19,58,448/- | 28-12-2011' | Two | 24-02-2012' | 25-02-2012' | 4 | 150 | 1) Surya Cable 2) Nisha cables 3) Mentor cables 4)Appolo Elec cor. | NIL | 25.06.2012' | APO::16.8.12 LOO:24.8.12 | 28.09.2012 06/10/2012 | Yes | (1) MTNM/MMII/PO-15//2012-13 (2) MTNM/MMII/PO-17/2012-13 | (1) Surya Cables (2) Nisha Cables. | 50 Kms 26 kms. | L-1 27850 L-II 27314.42 L-III 27850.0 | L1)Rs.1654793.5/- L2)Rs.858676.67/- L3 to be issued | Material Received. | Rs. 1654793.5
Sept., 2012 | 15 | 234 | SM(MM-II) | JT/KIT TSF-7 | MTNM/MM-II/ SDE(I&C)/15-98/ TSF-VII/2011-12 | Open | 1150 Nos | 43,55,567/- | 27-04-2012' | Two | 04/06/2012' | 05-06-2012' | 3 | 150 | 1) Rohit Corpo 2) Siehem | 1) Jas Technology | 17-07-2012' | 06.08.12 07.08.12(LOO) | 20.09.2012' | Yes | MTNM/MMII/PO-13//2012-13 Dated 20.09.12 &MTNM/MMII/PO-16//2012-13 Dated 20.09.12 | 1) Rohit Corpo 2) Siehem | LI=808 LII=345 | 3410/- | 1.Rs.2953948.31 2.Rs.1265977.85 | 21-10-2012' | Rs. 4219926.16
| 16 | 152 | SM(MM-II) | 100 PR CT BOX (CONN TYPE) | MTNM/MM-II/ DM(TICP-II)/14-12/ 11-12 | Open. | 1200 Nos | 9,82,800/- | 2012-01-21 | Two | 19-03-2012' | 20-03-2012' | 2 | 150 | 1)India tele & electric 2)Malson Electronics | NIL | 22-06-2012' | APO-25/07/2012 | 04-09-2012' | Yes | MTNM/MM-II/ DM(TICP-II)/14-12/2011-12 Dtd. 04/09/2012 | 1)India tele & electric 2)Malson Electronics | 1200 NOS. | 776.3 | 982795.8 | 29-10-2012' | Rs. 982795.8
Oct., 2012 |  | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Nov., 2012 | 17 | 254 | SM (MM-II) | Jointing Kits, TSF-V | MTNM/MM-II/ DM(I&C)/15-98/ TSF-V/2011-12 | Open. | 650 Nos. | 8,39,358/- | 16-08-2012' | Two | 20-09-2012' | 21-09-2012' | 4 | 150 | 1) JAS Technologies. 2) Siechem 3) Merritronix Pvt Ltd 4) Sunrise Telecom | NIL | 11.10.2012 | 22.10.12 | 22-11-2012' | Yes | MTNM/MMII/PO-13//2012-13 Dated 20.09.12 &MTNM/MMII/PO- | JAS Technologies | 8 | 1175/- | 878274.31 | 05-01-2013' | Rs. 878274.31
Dec., 2012 | 18 | 466 | SM (MM-II) | Jointing Kits, TSF-I | MTNM/SM(MM- II)/DM(I&C )/ 15-98/TSF-I/2012-13. | Open. | 500 Nos. | 2,28,060/- | 06-10-2012' | Two | 14-11-2012' | 14-11-2012' | 4 | 150 | 1) JAS Technologies. 2) Siechem 3) Sunrise Telecom | 1)Merritronix Pvt Ltd | 01-12-2012' | 2012-12-12 | 26-12-2012' | yes | 1) MTNM/MMII/PO-20/2012-13 dated-26-12-12 | 1)JAS TECHNOLOGIES | 500 Nos. | Rs.278/- | Rs.158376.60 | 07-02-2013' | Rs. 158376.60
Jan., 2013 | 19 | 464 | SM(MM-III) | Two way Speaker clip feature phone with RJ-11 female Jack | SM(MM-III)/ 13-44/Clip Phone/2012-13 | Open. | 100000 Nos | 4,52,03,000 | 01-11-2012' | Two | 07-12-2012' | 07-12-2012' | 1 | 150 | Pramod Telecom Pvt. Ltd. | Nil | 18-12-2012' | 2012-12-27 | 16-01-2013' | Yes | SM(MM-III)/13-44/Clip Phone/2012-13 Dated-16-01-2013 | Pramod Telecom Pvt. Ltd. | 75000 Nos. | Rs.537.51 | Rs.40313250.00 | 1.18-3-2013 2.16-05-2013 3.15-07-2013 | Rs. 40313250.00
| 20 | 236 | SM(MM-II) | Jointing Kits, TSF-VI | MTNM/MM-II/DM(I&C)/15-98/ TSF-VI/2011-12 | Open. | 1700 Nos. | 49,39,299/- | 06-09-2012' | Two | 15-10-2012' | 16-10-2012' | 5 | 150 | 1) JAS Technologies. 2) Siechem 3)Merritronix Pvt Ltd 4)Sunrise Telecom 5)Rohit Corporation | NIL | 05-11-2012' | 2012-12-22 | 11-01-2013' | Yes | 1)MTNM/MM-II/P-21/2012-13 Dated-11-01-13 2)MTNM/MM-II/P-22/2012-13 Dated-19-01-13 3)MTNM/MM-II/P-23/2012-13 Dated-05-03-13 | 1)Merritronix Pvt Ltd 2)M/s Sunrise Telecom 3)Merritronix Pvt Ltd | 1)850 Nos 2)482Nos. 3)368 Nos. | Rs.1437.92 | 1)Rs.13,55,733.35 2)Rs.7,68,780.67 3)Rs.5,86,952.87 | 1)10-03-2013 2)15-03-2013 3)20-04-2013 | Rs. 27,11,466.89
Feb. 2013 | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---' | ---'
Mar. 2013 | 21 | N/A | SM(MM-I) | Hired Vehicles. (LMCV) | MTNM/SM(MM-I)/DM(I/C,A)/RCT/17-17/2012-13. | Open. | 196 Nos. | 44727343 | 31-12-2012' | Two | 21-01-2013' | 21-01-2013' | 9 | 150 | (1) M/s New Way Travels. (2) M/s Good Luck Travels. (3) M/s Amit Travels (4) M/s Manish Travels. | (1) M/s Vivek Travels, (2) M/s D.C.Gupta Travels, (3) Vayudoot Travels, (4) M/s Aditya Travels, (5) M/s Manish Travels | 21-01-2013' | 25-03-2013' | R/C Dtd. 30/03/2013. | Yes. | MTNM/SM(MM-I)/DM(I/C,A)/RCT/17-17/2012-13. | (1) M/s New Way Travels. (2) M/s Good Luck Travels. (3) M/s Amit Travels (4) M/s Manish Travels. | 78 Nos. 41 Nos., 40 Nos., 37 Nos. | 7/- per kms. | R/c | Valid upto 32/03/2014 | R/C
- | 22 | N/A | SM(MM-III) | ILD Tender. (International Long Distance) Carrier Charges. | MTNM/MBI/ILD Carrier Charges/2012-11. | Open. | Not Applicable. | Transction Charges Rs.2 Crores per month. (approx) | Tender Technical Bid opened during 2010.However Price Bid is reviewed every quarterly & PO issued accordingly. | N/A | N/A | Price Bid reviewed every quarterly. | 3 | N/A | (1) M/s Relience Communications Ltd. (M/s RCL) (2) M/s Tata Communications Ltd. (TCL). (3) M/s Vodaphone South Ltd. | ---' | Price bid is opened every quarterly. | ---' | P.O. is issued every quarterly to L1 Bidders. | Yes. | P.O. is issued every quarterly to L1 Bidders. | (1) M/s Relience Communications Ltd. (M/s RCL) (2) M/s Tata Communications Ltd. (TCL). (3) M/s Vodaphone South Ltd. | N/A | N/A | N/A | P.O. issued quarterly. | N/A